## BOM & Install Schedule
Bill of Material and Install Schedule - Contract #1
Instructions:
1) Contractor to populate cells with bright yellow coloring. All other cells protected and not modifiable.
2) Contractor to transfer relevant inputted and calculated information to bid form confirming Total Contract Price is the same on this worksheet and the Bid Form.
3) Contractor to return worksheet (as an electronic worksheet, not PDF) with bid submittal.
Base Scope of Work
Line | Upgrade Action | Manufacturer | Part # | Total Luminaire Quantity | Pre-Negotiated Material Unit Price/ Luminaire | Pre- Negotiated Material Total Price | Contractor Material Markup % | Contractor Total Material Markup $ | Material Total Price with Contractor Markup | "Fully Loaded" Installation Unit Price/Luminaire | "Fully Loaded" Installation Total Price | Total Contract Price | Typical Crew Size/Truck (# of Techs/ Truck) | Weekly Crew Productivity (Luminaires/Week/Crew) | # of Crews Available to Commit to Project | Total Weekly Productivity
1 | Replace All Versions of Existing Selux Saturn Post-Top Luminaires (new luminaires will be installed on existing poles) | Cyclone Lighting | CLE17TD-NL-T5-P80-30K-10KV-R35-MVOLT-PTDR-BK-TX-CP7412 - fitter for 3.5 OD pole | 684 | 981.19 | 671133.96 |  | 0 | 671133.96 |  | 0 | 671133.96 |  |  |  | 0 | 26 | 20 kV SP? Pole Fitter? | 0
2 | Replace All Versions of Existing Selux Saturn Post-Top Luminaires (new luminaires will be installed on existing poles with twin arm brackets) | Cyclone Lighting | CLE17TD-NL-T5-P80-30K-10KV-R35-MVOLT-PTDR-BK-TX-CP7412 - fitter for 3.5 OD pole | 146 | 981.19 | 143253.74 |  | 0 | 143253.74 |  | 0 | 143253.74 |  |  |  | 0 |  |  | 0
3 | Install NLC on Above New Luminaires (material only, install included with luminaire line item) | Ubicquia | UBC-40-0-01-NA-01-02-TR | 830 | 138.03 | 114564.9 |  | 0 | 114564.9 | include above | 0 | 114564.9 | include above | include above | include above | include above
Total |  |  |  |  | 1119.22 | 928952.6 |  | 0 | 928952.6 |  | 0 | 928952.6 | <<<< This is the Total Contract Price that should be entered on the Bid Form
Pre-Approved Field Change Orders
Line | Upgrade Action | Description | [7 empty] | "Fully Loaded" Installation Unit Price | Quantity | Total Change Order Price
1 | Pole Rewire | If unsafe wiring is identified during installation, contractor shall replace wiring to meet any relevant code requirements. Unit pricing should include all costs associated with labor and miscellaneous materials (e.g. wire, wire connectors, etc.). It is expected this work would be completed at the time of luminaire installation and should not be priced as a separate trip to that location. All poles for this project scope are fed underground and max wire length associated with pole height is 14'. | [8 empty] | TBD During Installation | TBD During Installation